## Summary
FINRA — Open Work Report
Jira (megatron) · as of 14 Oct 2026 · In Progress, Needs Analysis, To Do
Open FINRA tickets | In Progress | Needs Analysis | To Do | Prod Pod | Hours logged
131 | 19 | 6 | 106 | 2 | 52
Status | Prod Pod | Other FINRA | Total | Assignee | Tickets | Team | Hours
In Progress | 0 | 19 | 19 | Shibi Ramaiyan | 2 | Prod Pod | 4
Needs Analysis | 1 | 5 | 6 | Abiola Banjoko | 1 | Other | 0
To Do | 1 | 105 | 106 | Bleta Jashari | 8 | Other | 0
Total | 2 | 129 | 131 | Corinne Tighe | 1 | Other | 0
|  |  |  | Dalvinder Grewal | 1 | Other | 0
|  |  |  | James Simmons | 8 | Other | 0
|  |  |  | Mansi Chadha | 1 | Other | 0
|  |  |  | Milan Dusara | 1 | Other | 0
|  |  |  | Mitali Bhavsar | 3 | Other | 0
|  |  |  | Pavan Vemunuri | 1 | Other | 21
|  |  |  | Prabhjot Singh | 1 | Other | 0
|  |  |  | Rohith Kunnilethu | 1 | Other | 8
|  |  |  | Ryo Poc | 2 | Other | 0
|  |  |  | Sanchivan Sivadasan | 1 | Other | 5
|  |  |  | Satwinder Randhawa | 5 | Other | 0
|  |  |  | Thiva Varatharajah | 1 | Other | 0
|  |  |  | Timothy Chiang | 2 | Other | 1
|  |  |  | Unassigned | 91 | Other | 13
How tickets were selected
• Current status is In Progress, Needs Analysis or To Do.
• Client field = FINRA, “FINRA” or the “FIN -” project prefix in the title, or a FINRA / “FIN -” parent ticket; titles, descriptions and comments were all searched.
• Prod Pod = tickets assigned to Shibi Ramaiyan or Yetunde Sanusi.
• Notes flag tickets with no update in over 90 days, multi-client tickets and subtasks.
• The ‘For Review’ tab lists 4 multi-client tickets not counted: 3 ETL 2.0 pilot tickets and IR-907 (reporting issue across 10 clients).
• Not counted: CR-489 (DEL), MEG-33053, MEG-21407 and MEG-28712 (Block/BMO) and MEG-24951 (cancelled GBC clone), which only mention FINRA or FIN in passing.
• Hours Logged is the total time logged on each ticket in Jira, all time, including subtasks. Epics count only their own time; child-ticket hours are in the Notes column so nothing is counted twice.
• Last Updated is the ticket's last-updated date in Jira. Totals are live formulas over the Prod Pod and Other FINRA tabs.

## Prod Pod
Prod Pod — FINRA Open Work
Assignee: Shibi Ramaiyan or Yetunde Sanusi · as of 14 Oct 2026
Ticket | Summary | Status | Reporter | Assignee | Last Updated | Hours Logged | Notes
IP-3012 | Upgrade the Microsoft Office 365 authentication method for Einstein Activity Capture | Needs Analysis | Shibi Ramaiyan | Shibi Ramaiyan | 2026-10-13 | 0 | Multi-client: Client field = Breakthru, FINRA, Anaplan, OPS
IP-2856 | FINRA: Financial Approver Visibility | To Do | Darci Frye | Shibi Ramaiyan | 2026-10-14 | 4
Total hours logged | [5 empty] | 4

## Other FINRA
Other FINRA Open Work
All remaining open FINRA tickets, including unassigned · as of 14 Oct 2026
Ticket | Summary | Status | Reporter | Assignee | Last Updated | Hours Logged | Notes
MEG-18805 | FIN - Discovery | In Progress | Ryan Quesnel | Unassigned | 2025-03-05 | 13 | Hours include child tickets · No update in 588 days
MEG-19584 | FIN - Data Migration / Load Sheets (PROD) - Business Validation | In Progress | David Kong | Bleta Jashari | 2025-06-18 | 0 | No update in 483 days
MEG-19591 | FIN - Data Migration / Load Sheets (PROD) - Dev Uploads | In Progress | David Kong | Dalvinder Grewal | 2025-04-29 | 0 | No update in 533 days
MEG-19723 | FIN - SIT & Regression Testing (Test/Staging) - QA | In Progress | David Kong | Mitali Bhavsar | 2025-05-14 | 0 | No update in 518 days
MEG-19851 | PH-To Test Auto-calculate OT rates on Engagement Assignment and on Convert to Engagement | In Progress | Suman Dsa | Unassigned | 2025-12-01 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 317 days
MEG-19852 | PH- To Test if Users are prevented from cloning Vendor Sourced Or Payroll, Engagement Assignments | In Progress | Suman Dsa | Unassigned | 2025-12-01 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 317 days
MEG-19853 | PH- To Test view/edit access of users (VMO MSP, HM and Suppliers) on Rate object on assignment | In Progress | Suman Dsa | Unassigned | 2025-12-01 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 317 days
MEG-19938 | ASSUMPTION - Master Data Files sync'ing daily | In Progress | David Kong | Bleta Jashari | 2025-07-10 | 0 | Under MEG-18947 FIN - PROD Cutover Activities · No update in 461 days
MEG-20014 | To test Clone Engagement Assignment - HeadCount Assignments | In Progress | Mitali Bhavsar | Unassigned | 2025-12-01 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 317 days
MEG-20019 | To test Clone Engagement Assignment - Clone Assignments | In Progress | Mitali Bhavsar | Unassigned | 2025-12-03 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 315 days
MEG-20027 | To test Create Rate and Set Rate as Primary rate. | In Progress | Mitali Bhavsar | Unassigned | 2025-12-01 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 317 days
MEG-20107 | FIN - Setup DevOps Pipeline (to QA/FULL) | In Progress | Ryan Quesnel | Pavan Vemunuri | 2025-04-04 | 21 | Hours include child tickets · No update in 558 days
MEG-20258 | Provision API Access to Client | In Progress | Ryan Quesnel | Sanchivan Sivadasan | 2025-04-04 | 5 | Under MEG-19265 FIN - Client Training & Support of API · No update in 558 days
MEG-20651 | FIN - Integration Connectivity Instructions | In Progress | Timothy Chiang | Timothy Chiang | 2025-05-20 | 1 | No update in 512 days
STAR-1688 | FINRA Report/Dashboard prep | In Progress | Beth Bruder | Satwinder Randhawa | 2025-07-03 | 0 | No update in 468 days
STAR-1692 | “Starts” dashboard | In Progress | Satwinder Randhawa | Satwinder Randhawa | 2025-06-16 | 0 | Under STAR-1688 FINRA Report/Dashboard prep · No update in 485 days
STAR-1693 | “Ends” dashboard | In Progress | Satwinder Randhawa | Satwinder Randhawa | 2025-06-17 | 0 | Under STAR-1688 FINRA Report/Dashboard prep · No update in 484 days
STAR-1694 | Supplier Performance dashboard | In Progress | Satwinder Randhawa | Satwinder Randhawa | 2025-06-16 | 0 | Under STAR-1688 FINRA Report/Dashboard prep · No update in 485 days
STAR-1695 | Location tracking | In Progress | Satwinder Randhawa | Satwinder Randhawa | 2025-06-10 | 0 | Under STAR-1688 FINRA Report/Dashboard prep · No update in 491 days
IP-1793 | FINRA - Managers receiving Approval Emails even though approval is not in their queue | Needs Analysis | Milan Dusara | Abiola Banjoko | 2025-10-14 | 0 | No update in 365 days
MEG-19721 | FIN - Deployment from Test/Staging to PROD | Needs Analysis | David Kong | Unassigned | 2025-04-16 | 0 | No update in 546 days
MEG-19724 | FIN - (Targeted) Regression Testing (PROD) | Needs Analysis | David Kong | Mitali Bhavsar | 2025-04-16 | 0 | No update in 546 days
MEG-20025 | To test Manual Add adjustments. | Needs Analysis | Mitali Bhavsar | Unassigned | 2025-12-04 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 314 days
MEG-20026 | To test Clone transaction | Needs Analysis | Mitali Bhavsar | Unassigned | 2025-12-01 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 317 days
CR-1027 | FINRA: Auto‑Populate Offer End Date Based on Offer Start Date | To Do | Darci Frye | Unassigned | 2026-01-21 | 0 | No update in 266 days
CR-1045 | FINRA: What field is determines the locations on the integration? | To Do | Darci Frye | Unassigned | 2026-02-24 | 0 | No update in 232 days
CR-1155 | In FINRA Prod, Open Date/Time field is being overwritten when Req Assignment status is changed from Open to Draft/In Review to add new vendors and then changed to Open again | To Do | Satwinder Randhawa | Unassigned | 2026-03-31 | 0 | No update in 197 days
CR-1263 | FINRA: Supplier Attributes Updated to IT Preferred | To Do | Darci Frye | Unassigned | 2026-06-16 | 0 | No update in 120 days
CR-1268 | FINRA: Central Notification Center (Suppliers & Managers) | To Do | Darci Frye | Unassigned | 2026-06-16 | 0 | No update in 120 days
CR-1284 | FINRA: Delegation Visibility | To Do | Darci Frye | Unassigned | 2026-06-24 | 0 | No update in 112 days
CR-1285 | FINRA: PO dates extended via Extension Workflow | To Do | Darci Frye | Unassigned | 2026-06-24 | 0 | No update in 112 days
CR-1316 | FINRA: Update Case Visibility for HM | To Do | Darci Frye | Unassigned | 2026-07-16 | 0
CR-1338 | FINRA: Jake Galbrith Dashboard Creation Access | To Do | Darci Frye | Unassigned | 2026-07-29 | 0
CR-1381 | FINRA: 1074 Approval Authority – Supervisory Organization Manager Decoupling Review | To Do | Darci Frye | Unassigned | 2026-08-26 | 0
CR-1421 | FINRA: Supplier Task and Approval Notification Enhancements | To Do | Darci Frye | Unassigned | 2026-09-30 | 0
CR-859 | FIN - Clean up redundant position fields on the assignment and redundant position records | To Do | Timothy Chiang | Unassigned | 2025-10-01 | 0 | No update in 378 days
IP-2525 | FINRA: Send to Workday Error Message | To Do | Darci Frye | Unassigned | 2026-04-15 | 0 | No update in 182 days
IP-2879 | FINRA - When they rehire, the wizard creates a duplicate contrator contact | To Do | Timothy Chiang | Milan Dusara | 2026-06-22 | 0 | No update in 114 days
IP-3022 | FINRA: Requisition Filled Email- Sending twice | To Do | Darci Frye | Unassigned | 2026-08-06 | 0
IP-3170 | FIN - Birthdays in dataloaded legacy contractors have the wrong birthdays | To Do | Timothy Chiang | Unassigned | 2026-09-29 | 0
IR-447 | Expense Report Approval Delegation – Handling End of Delegation Period (In-Flight Approvals) | To Do | Mitali Bhavsar | Ryo Poc | 2026-03-25 | 0 | No update in 203 days
IR-450 | FINRA - Callout Record Analysis | To Do | Milan Dusara | Unassigned | 2025-07-22 | 0 | No update in 449 days
IR-461 | FINRA - Training to Schedule Reports | To Do | Milan Dusara | Corinne Tighe | 2025-08-11 | 0 | No update in 429 days
IR-481 | FIN - Disabled Before Trigger Flow Analysis and Fix | To Do | Timothy Chiang | Mansi Chadha | 2025-09-17 | 0 | No update in 392 days
IR-493 | FIN - Handle outstanding assignments that need to be retriggered | To Do | Timothy Chiang | Unassigned | 2026-03-25 | 0 | No update in 203 days
IR-494 | FIN - Business to decide if contacts is an issue | To Do | Timothy Chiang | Unassigned | 2026-03-25 | 0 | No update in 203 days
IR-495 | FIN - Handle outstanding cases that need to be retriggered | To Do | Timothy Chiang | Unassigned | 2026-03-25 | 0 | No update in 203 days
IR-496 | FIN - Business to decide if rates is an issue | To Do | Timothy Chiang | Unassigned | 2026-03-25 | 0 | No update in 203 days
IR-497 | FIN - Business to decide if tasks (finger printing) is an issue | To Do | Timothy Chiang | Unassigned | 2026-03-25 | 0 | No update in 203 days
IR-812 | FINRA - can we please have Inbound Integration Record in Timesheet quick links | To Do | Katy Godfrey | Unassigned | 2026-04-10 | 0 | No update in 187 days
MEG-18880 | FIN - Business | To Do | Corinne Tighe | Unassigned | 2025-02-25 | 0 | Epic · No update in 596 days
MEG-18920 | FIN - Configuration | To Do | David Kong | Unassigned | 2025-01-09 | 0 | Epic · 0.5 h logged across its child tickets (not counted) · No update in 643 days
MEG-18923 | FIN - REQ Wizard | To Do | David Kong | Unassigned | 2025-03-03 | 0 | Epic · 49.75 h logged across its child tickets (not counted) · No update in 590 days
MEG-18924 | FIN - Requisitions | To Do | David Kong | Unassigned | 2025-01-09 | 0 | Epic · 37 h logged across its child tickets (not counted) · No update in 643 days
MEG-18925 | FIN - Transactions / Invoicing | To Do | David Kong | Unassigned | 2025-01-09 | 0 | Epic · 18.5 h logged across its child tickets (not counted) · No update in 643 days
MEG-18926 | FIN - Approvals (spend) | To Do | David Kong | Unassigned | 2025-01-31 | 0 | Epic · 95 h logged across its child tickets (not counted) · No update in 621 days
MEG-18927 | FIN - Unit Sheet (VMS) | To Do | David Kong | Unassigned | 2025-01-09 | 0 | Epic · 4 h logged across its child tickets (not counted) · No update in 643 days
MEG-18928 | FIN - Expense | To Do | David Kong | Unassigned | 2025-01-24 | 0 | Epic · 66.25 h logged across its child tickets (not counted) · No update in 628 days
MEG-18929 | FIN - On Boarding / Off boarding | To Do | David Kong | Unassigned | 2025-01-09 | 0 | Epic · 48.5 h logged across its child tickets (not counted) · No update in 643 days
MEG-18931 | FIN - Custom Reports | To Do | David Kong | Unassigned | 2025-01-09 | 0 | Epic · 0.5 h logged across its child tickets (not counted) · No update in 643 days
MEG-18932 | Standard Reports | To Do | David Kong | James Simmons | 2025-03-06 | 0 | Under MEG-18880 FIN - Business · No update in 587 days
MEG-18933 | Dashboards | To Do | David Kong | James Simmons | 2025-03-06 | 0 | Under MEG-18880 FIN - Business · No update in 587 days
MEG-18934 | Field Tracking | To Do | David Kong | James Simmons | 2025-03-06 | 0 | Under MEG-18880 FIN - Business · No update in 587 days
MEG-18937 | FIN - Profile / User Roles | To Do | David Kong | Unassigned | 2025-03-03 | 0 | Epic · 28 h logged across its child tickets (not counted) · No update in 590 days
MEG-18938 | FIN - Submission / Candidate | To Do | David Kong | Unassigned | 2025-02-28 | 0 | Epic · 189.75 h logged across its child tickets (not counted) · No update in 593 days
MEG-18939 | FIN - Engagement Management | To Do | David Kong | Unassigned | 2025-04-08 | 0 | Epic · 173.25 h logged across its child tickets (not counted) · No update in 554 days
MEG-18941 | FIN - Integration - Timesheets | To Do | David Kong | Unassigned | 2025-05-09 | 0 | Epic · 122 h logged across its child tickets (not counted) · No update in 523 days
MEG-18942 | FIN - Integration - Master Data (SFTP) | To Do | David Kong | Unassigned | 2025-03-03 | 0 | Epic · 160 h logged across its child tickets (not counted) · No update in 590 days
MEG-18943 | FIN - Integration - New Hire / Rehire - Workday (API) | To Do | David Kong | Unassigned | 2025-01-31 | 0 | Epic · 98.0333 h logged across its child tickets (not counted) · No update in 621 days
MEG-18945 | FIN - Integration - Workday Financials (XML) | To Do | David Kong | Unassigned | 2025-01-31 | 0 | Epic · 40 h logged across its child tickets (not counted) · No update in 621 days
MEG-18947 | FIN - PROD Cutover Activities | To Do | David Kong | Unassigned | 2025-04-16 | 0 | Epic · 0.5 h logged across its child tickets (not counted) · No update in 546 days
MEG-18948 | FIN - Go-Live | To Do | David Kong | Unassigned | 2025-03-04 | 0 | Epic · 10 h logged across its child tickets (not counted) · No update in 589 days
MEG-18955 | Setup MSP User | To Do | David Kong | James Simmons | 2025-03-06 | 0 | Under MEG-18880 FIN - Business · No update in 587 days
MEG-18956 | Setup Payroll Supplier - Account & Contact | To Do | David Kong | James Simmons | 2025-03-06 | 0 | Under MEG-18880 FIN - Business · No update in 587 days
MEG-19147 | FIN - Integrations - Other | To Do | David Kong | Unassigned | 2025-02-25 | 0 | Epic · 61 h logged across its child tickets (not counted) · No update in 596 days
MEG-19158 | Setup Holiday Schedule - 2025 and 2026 | To Do | David Kong | James Simmons | 2025-03-06 | 0 | Under MEG-18880 FIN - Business · No update in 587 days
MEG-19192 | FIN - Integration Connectivity | To Do | Ryan Quesnel | Unassigned | 2025-01-23 | 0 | Epic · 28 h logged across its child tickets (not counted) · No update in 629 days
MEG-19200 | FIN Regression Test | To Do | Mitali Bhavsar | Unassigned | 2025-12-01 | 0 | QA test set · No update in 317 days
MEG-19224 | FIN - Data Migration (load sheets) | To Do | David Kong | Unassigned | 2025-01-31 | 0 | Epic · No update in 621 days
MEG-19225 | Test / UAT Load Sheet | To Do | David Kong | Unassigned | 2025-01-31 | 0 | Under MEG-19224 FIN - Data Migration (load sheets) · No update in 621 days
MEG-19226 | Production Load Sheet | To Do | David Kong | Unassigned | 2025-01-31 | 0 | Under MEG-19224 FIN - Data Migration (load sheets) · No update in 621 days
MEG-19263 | FIN - Integration - Termination and Change HM (API) | To Do | David Kong | Unassigned | 2025-04-01 | 0 | Epic · 11 h logged across its child tickets (not counted) · No update in 561 days
MEG-19299 | FIN - Integration Workflow Scenarios | To Do | Ryan Quesnel | Unassigned | 2025-02-28 | 0 | Epic · 152.333 h logged across its child tickets (not counted) · No update in 593 days
MEG-19365 | Email Templates / Triggers | To Do | David Kong | James Simmons | 2025-03-06 | 0 | Under MEG-18880 FIN - Business · No update in 587 days
MEG-19374 | FIN - Add Interviewer - Whenever new Interview request is created HM should be auto -added to the list of interviewers | To Do | Mitali Bhavsar | Rohith Kunnilethu | 2025-08-21 | 8 | No update in 419 days
MEG-19418 | FIN - Rename MSP everywhere in email templates to VMO (FINRA terminology) | To Do | David Kong | Bleta Jashari | 2025-05-02 | 0 | No update in 530 days
MEG-19440 | FIN - Phase 2 | To Do | David Kong | Unassigned | 2025-02-14 | 0 | Epic · No update in 607 days
MEG-19585 | FIN - Data Migration / Load Sheets (PROD) - IT Validation | To Do | David Kong | Bleta Jashari | 2025-04-16 | 0 | No update in 546 days
MEG-19598 | FIN - Strip off all [x] Deprecated field visibility all users | To Do | David Kong | Bleta Jashari | 2025-02-28 | 0 | No update in 593 days
MEG-19699 | FIN - Integration - Worker Updates - Workday (API) | To Do | David Kong | Unassigned | 2026-03-13 | 0 | Epic · 14 h logged across its child tickets (not counted) · No update in 215 days
MEG-19718 | FIN - QA/FULL Deployment & Regression Activities | To Do | David Kong | Unassigned | 2025-04-16 | 0 | Epic · 4 h logged across its child tickets (not counted) · No update in 546 days
MEG-19856 | FINAL position list (100% complete) | To Do | David Kong | James Simmons | 2025-03-06 | 0 | No update in 587 days
MEG-19857 | To Test Spend Approvals on Assignments- End To End (Regular + Etensions) | To Do | Suman Dsa | Unassigned | 2025-12-01 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 317 days
MEG-19944 | FIN - All integration connections / Master Data for PROD | To Do | David Kong | Unassigned | 2025-04-16 | 0 | No update in 546 days
MEG-19964 | FIN - Client Integration Work | To Do | David Kong | Unassigned | 2025-05-02 | 0 | Epic · No update in 530 days
MEG-19970 | FIN - Client must schedule Timesheet 1119 and 1120 files to drop to QA SFTP | To Do | David Kong | Bleta Jashari | 2025-05-14 | 0 | No update in 518 days
MEG-20087 | FIN - Setup Dev Environment | To Do | Ryan Quesnel | Unassigned | 2025-03-20 | 0 | Epic · 5 h logged across its child tickets (not counted) · No update in 573 days
MEG-20143 | FIN - Client to execute / plan for go-live migration (Fieldglass ID's - WK and WO) | To Do | David Kong | Bleta Jashari | 2025-05-02 | 0 | No update in 530 days
MEG-20230 | Internal - To test Cancel Req- Category Screen | To Do | Mitali Bhavsar | Unassigned | 2025-12-01 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 317 days
MEG-20231 | Internal -To test Cancel Req -Assignment Screen | To Do | Mitali Bhavsar | Unassigned | 2025-12-01 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 317 days
MEG-20232 | Internal- To test Cancel Req -Position Screen | To Do | Mitali Bhavsar | Unassigned | 2025-12-01 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 317 days
MEG-20233 | Internal -To test if Closing Date/time is added to a Requisition with status "Draft"/"In Review" then Requisition status is updated based on inputted Closing Date/time. | To Do | Mitali Bhavsar | Unassigned | 2025-12-02 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 316 days
MEG-20234 | Internal -To test if Closing Date/time is added to a Requisition with status "Open" then Requisition status is updated based on inputted Closing Date/time . | To Do | Mitali Bhavsar | Unassigned | 2025-12-02 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 316 days
MEG-20235 | Internal - To test if Vendor is unable to Create/Submit a Candidate Record when Requisition status is Evaluation, Filled, On Hold or Cancelled | To Do | Mitali Bhavsar | Unassigned | 2025-12-02 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 316 days
MEG-20236 | Internal - To Test if Vendor is able to withdraw a Candidate and then resubmit the candidate. | To Do | Mitali Bhavsar | Unassigned | 2025-12-02 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 316 days
MEG-20237 | Internal - To test if Vendor is able to deny an interview request-Place holder | To Do | Mitali Bhavsar | Unassigned | 2025-12-01 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 317 days
MEG-20238 | Internal- To Test validation error message for Req Interview and Make Offer (HM) Button | To Do | Mitali Bhavsar | Unassigned | 2025-12-01 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 317 days
MEG-20239 | Internal - To test if Partial Match is applied when supplier is accepting an offer for a Candidate such that the Candidate's Email ID matches with Existing Contractor Email ID and Candidate ID doesnot match with existing Contractor's Candidate ID | To Do | Mitali Bhavsar | Unassigned | 2025-12-01 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 317 days
MEG-20240 | Internal - To test if Partial Match is applied when supplier is accepting an offer for a Candidate such that the Candidate's Email ID doesnot match with Existing Contractor Email ID and Candidate ID matches with existing Contractor's Candidate ID | To Do | Mitali Bhavsar | Unassigned | 2025-12-03 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 315 days
MEG-20294 | FINRA Dev/QA Test Cycle1 April 2025 | To Do | Mitali Bhavsar | Prabhjot Singh | 2025-12-01 | 0 | QA test execution · No update in 317 days
MEG-20318 | To test Approval Delegations | To Do | Mitali Bhavsar | Unassigned | 2025-12-01 | 0 | QA test · Under MEG-20726 FIN-QA Testing · No update in 317 days
MEG-20724 | FIN Regression Test | To Do | Mitali Bhavsar | Mitali Bhavsar | 2025-12-01 | 0 | QA test execution · No update in 317 days
MEG-20726 | FIN-QA Testing | To Do | Mitali Bhavsar | Unassigned | 2025-12-01 | 0 | Epic · No update in 317 days
MEG-20812 | PH - FIN - To test Assignment Expiry Email Notifications | To Do | Suman Dsa | Unassigned | 2025-12-01 | 0 | QA test · No update in 317 days
MEG-20813 | PH - FIN - To test PO Depletion Email notifications | To Do | Suman Dsa | Unassigned | 2025-12-04 | 0 | QA test · No update in 314 days
MEG-20945 | FIN - SIT Issues | To Do | Ryan Quesnel | Unassigned | 2025-05-14 | 0 | Epic · 23.5167 h logged across its child tickets (not counted) · No update in 518 days
MEG-21328 | FIN - Change Request - Invoice Automation | To Do | Corinne Tighe | Bleta Jashari | 2025-05-30 | 0 | No update in 502 days
MEG-21782 | (Sample-FINRA Critical and High Risk Test Scenarios Set) | To Do | Prabhjot Singh | Unassigned | 2025-06-17 | 0 | QA test set · No update in 484 days
MEG-21937 | (Sample)-FIN-Placeholder Test Plan- Short Term | To Do | Mitali Bhavsar | Unassigned | 2025-12-01 | 0 | QA test plan · No update in 317 days
MEG-21938 | (Sample-FIN-Placeholder Test Execution- Short Term) | To Do | Mitali Bhavsar | Unassigned | 2025-12-01 | 0 | QA sub test execution · No update in 317 days
MEG-21939 | FIN -Placeholder Test | To Do | Mitali Bhavsar | Unassigned | 2025-06-13 | 0 | QA test · No update in 488 days
MEG-21979 | FIN - Test Cycle - Training June 2025 | To Do | Mitali Bhavsar | Unassigned | 2025-12-01 | 0 | QA test execution · No update in 317 days
MEG-22118 | FINRA - Bill Rate not exposed to supplier | To Do | Corinne Tighe | Unassigned | 2025-06-19 | 0 | No update in 482 days
MEG-22141 | FIN-SOW/Headcount Eng-A-New fields are showing on Eng-Assignment | To Do | Thiva Varatharajah | Thiva Varatharajah | 2025-07-11 | 0 | No update in 460 days
MEG-22234 | FIN - Workday Production Connectivity Test | To Do | Ryan Quesnel | Timothy Chiang | 2025-06-25 | 0 | No update in 476 days
MEG-22495 | FIN- Refresh full? Discuss | To Do | Bleta Jashari | Unassigned | 2025-10-28 | 0 | No update in 351 days
MEG-22540 | FIN-Eng-Assignment- MSP should be allowed to close all tasks | To Do | Thiva Varatharajah | Ryo Poc | 2025-07-11 | 0 | No update in 460 days
STAR-1689 | Functional standard reports and dashboards library with all necessary custom reporting fields | To Do | Satwinder Randhawa | Unassigned | 2025-06-10 | 0 | Under STAR-1688 FINRA Report/Dashboard prep · No update in 491 days
STAR-1696 | FINRA specific reporting | To Do | Satwinder Randhawa | Unassigned | 2025-06-10 | 0 | No update in 491 days
Total hours logged | [5 empty] | 48

## For Review
For Review — Not Counted in Totals
Multi-client tickets that include FINRA work; decide whether to include
Ticket | Summary | Status | Reporter | Assignee | Last Updated | Hours Logged | Notes
CBT-137 | .NET build of the three evaluation scenarios (FINRA 400, Rogers Freelancers, Anaplan P1000 Employees) | In Progress | mohsinb | mohsinb | 2026-10-13 | 0 | Multi-client ETL 2.0 pilot: FINRA 400 is one of three scenarios
CBT-85 | Define pilot exit criteria and reconciliation method | In Progress | mohsinb | mohsinb | 2026-10-13 | 0 | Multi-client ETL 2.0 pilot: scorecard covers FINRA 400, Rogers Freelancers and Anaplan P1000
CBT-97 | Assess ADF-native versus Functions per pilot workload | In Progress | mohsinb | mohsinb | 2026-10-13 | 0 | Multi-client ETL 2.0 pilot: workloads include FINRA 400 and Rogers 1500
IR-907 | Verify Your Identity Prompt When Exporting Reports - Wrong Report Output than Selected | To Do | Darci Frye | Unassigned | 2026-07-22 | 0 | Multi-client: FINRA is one of 10 clients affected (with Anaplan, Deloitte, FanDuel, KPMG, PwC and others)
Total hours logged | [5 empty] | 0